## Country_1
Country_1 M&E Tracker
Output Indicator ID | Output Indicator Description | Activity ID | Activity Name | Component | Country of Implementation | Start Date | End Date | Program Year | Quarter of Implementation | Planned Number of Participants | Actual Number of Participants | % Achievement | Means of Verification (Primary) | Use Second Verification? (Yes/No) | Status | Comments / Risks / Issues
OI-101 | People trained in targeted skills | C1A001 | Training workshop 1 | Training | Country_1 | 2024-01-01 | 2024-03-31 | Year 1 | Y1Q1 | 42 | 52 | 123.8% | Signed attendance sheet; pre/post test forms | No | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C1A002 | Community outreach campaign 2 | Outreach | Country_1 | 2024-04-01 | 2024-06-30 | Year 1 | Y1Q2 | 47 | 53 | 112.8% | Activity report; photo log | Yes | Completed | Completed as scheduled.
OI-103 | Supportive supervision visits conducted | C1A003 | Supportive supervision visit 3 | Monitoring | Country_1 | 2024-07-01 | 2024-09-30 | Year 1 | Y1Q3 | 52 | 54 | 103.8% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C1A004 | Policy dialogue 4 | Advocacy | Country_1 | 2024-10-01 | 2024-12-31 | Year 1 | Y1Q4 | 57 | 55 | 96.49% | Meeting minutes; participant list | No | In progress | Final attendance reconciliation pending.
OI-101 | People trained in targeted skills | C1A005 | Training workshop 5 | Training | Country_1 | 2025-01-01 | 2025-03-31 | Year 2 | Y2Q1 | 62 | 56 | 90.32% | Signed attendance sheet; pre/post test forms | Yes | In progress | Final attendance reconciliation pending.
OI-102 | Community outreach events delivered | C1A006 | Community outreach campaign 6 | Outreach | Country_1 | 2025-04-01 | 2025-06-30 | Year 2 | Y2Q2 | 67 | 57 | 85.07% | Activity report; photo log | No | In progress | Final attendance reconciliation pending.
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Country_1
Second Verification Tracker
Activity ID | Output Indicator ID | Second Verification Type | Verification Description | Verification Date | Verification Status | Verification File Reference / Link
C1A002 | OI-102 | Digital Verification | Digital Verification completed for C1A002 | 2024-07-14 | Complete | Ref/Country_1/C1A002
C1A005 | OI-101 | Phone Check | Phone Check scheduled / under review for C1A005 | 2025-04-14 | In Review | Ref/Country_1/C1A005

## Country_2
Country_2 M&E Tracker
Output Indicator ID | Output Indicator Description | Activity ID | Activity Name | Component | Country of Implementation | Start Date | End Date | Program Year | Quarter of Implementation | Planned Number of Participants | Actual Number of Participants | % Achievement | Means of Verification (Primary) | Use Second Verification? (Yes/No) | Status | Comments / Risks / Issues
OI-102 | Community outreach events delivered | C2A001 | Community outreach campaign 1 | Outreach | Country_2 | 2025-07-01 | 2025-09-30 | Year 2 | Y2Q3 | 49 | 41 | 83.67% | Activity report; photo log | Yes | In progress | Final attendance reconciliation pending.
OI-103 | Supportive supervision visits conducted | C2A002 | Supportive supervision visit 2 | Monitoring | Country_2 | 2025-10-01 | 2025-12-31 | Year 2 | Y2Q4 | 54 | 63 | 116.7% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C2A003 | Policy dialogue 3 | Advocacy | Country_2 | 2026-01-01 | 2026-03-31 | Year 3 | Y3Q1 | 59 | 64 | 108.5% | Meeting minutes; participant list | No | Completed | Completed as scheduled.
OI-101 | People trained in targeted skills | C2A004 | Training workshop 4 | Training | Country_2 | 2026-04-01 | 2026-06-30 | Year 3 | Y3Q2 | 64 | 65 | 101.6% | Signed attendance sheet; pre/post test forms | Yes | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C2A005 | Community outreach campaign 5 | Outreach | Country_2 | 2026-07-01 | 2026-09-30 | Year 3 | Y3Q3 | 69 | 0 | 0% | Activity report; photo log | No | Not started | Planned for a future quarter.
OI-103 | Supportive supervision visits conducted | C2A006 | Supportive supervision visit 6 | Monitoring | Country_2 | 2026-10-01 | 2026-12-31 | Year 3 | Y3Q4 | 74 | 0 | 0% | Supervision checklist; visit report | No | Not started | Planned for a future quarter.
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Country_2
Second Verification Tracker
Activity ID | Output Indicator ID | Second Verification Type | Verification Description | Verification Date | Verification Status | Verification File Reference / Link
C2A001 | OI-102 | Digital Verification | Digital Verification scheduled / under review for C2A001 | 2025-10-14 | In Review | Ref/Country_2/C2A001
C2A004 | OI-101 | Phone Check | Phone Check completed for C2A004 | 2026-07-14 | Complete | Ref/Country_2/C2A004

## Country_3
Country_3 M&E Tracker
Output Indicator ID | Output Indicator Description | Activity ID | Activity Name | Component | Country of Implementation | Start Date | End Date | Program Year | Quarter of Implementation | Planned Number of Participants | Actual Number of Participants | % Achievement | Means of Verification (Primary) | Use Second Verification? (Yes/No) | Status | Comments / Risks / Issues
OI-103 | Supportive supervision visits conducted | C3A001 | Supportive supervision visit 1 | Monitoring | Country_3 | 2024-01-01 | 2024-03-31 | Year 1 | Y1Q1 | 56 | 51 | 91.07% | Supervision checklist; visit report | No | In progress | Final attendance reconciliation pending.
OI-104 | Policy dialogues facilitated | C3A002 | Policy dialogue 2 | Advocacy | Country_3 | 2024-04-01 | 2024-06-30 | Year 1 | Y1Q2 | 61 | 52 | 85.25% | Meeting minutes; participant list | No | In progress | Final attendance reconciliation pending.
OI-101 | People trained in targeted skills | C3A003 | Training workshop 3 | Training | Country_3 | 2024-07-01 | 2024-09-30 | Year 1 | Y1Q3 | 66 | 74 | 112.1% | Signed attendance sheet; pre/post test forms | Yes | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C3A004 | Community outreach campaign 4 | Outreach | Country_3 | 2024-10-01 | 2024-12-31 | Year 1 | Y1Q4 | 71 | 75 | 105.6% | Activity report; photo log | No | Completed | Completed as scheduled.
OI-103 | Supportive supervision visits conducted | C3A005 | Supportive supervision visit 5 | Monitoring | Country_3 | 2025-01-01 | 2025-03-31 | Year 2 | Y2Q1 | 76 | 76 | 100% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C3A006 | Policy dialogue 6 | Advocacy | Country_3 | 2025-04-01 | 2025-06-30 | Year 2 | Y2Q2 | 31 | 27 | 87.1% | Meeting minutes; participant list | Yes | In progress | Final attendance reconciliation pending.
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Country_3
Second Verification Tracker
Activity ID | Output Indicator ID | Second Verification Type | Verification Description | Verification Date | Verification Status | Verification File Reference / Link
C3A003 | OI-101 | Phone Check | Phone Check completed for C3A003 | 2024-10-14 | Complete | Ref/Country_3/C3A003
C3A006 | OI-104 | Site Visit | Site Visit scheduled / under review for C3A006 | 2025-07-14 | In Review | Ref/Country_3/C3A006

## Country_4
Country_4 M&E Tracker
Output Indicator ID | Output Indicator Description | Activity ID | Activity Name | Component | Country of Implementation | Start Date | End Date | Program Year | Quarter of Implementation | Planned Number of Participants | Actual Number of Participants | % Achievement | Means of Verification (Primary) | Use Second Verification? (Yes/No) | Status | Comments / Risks / Issues
OI-104 | Policy dialogues facilitated | C4A001 | Policy dialogue 1 | Advocacy | Country_4 | 2025-07-01 | 2025-09-30 | Year 2 | Y2Q3 | 63 | 61 | 96.83% | Meeting minutes; participant list | No | In progress | Final attendance reconciliation pending.
OI-101 | People trained in targeted skills | C4A002 | Training workshop 2 | Training | Country_4 | 2025-10-01 | 2025-12-31 | Year 2 | Y2Q4 | 68 | 62 | 91.18% | Signed attendance sheet; pre/post test forms | Yes | In progress | Final attendance reconciliation pending.
OI-102 | Community outreach events delivered | C4A003 | Community outreach campaign 3 | Outreach | Country_4 | 2026-01-01 | 2026-03-31 | Year 3 | Y3Q1 | 73 | 63 | 86.3% | Activity report; photo log | No | In progress | Final attendance reconciliation pending.
OI-103 | Supportive supervision visits conducted | C4A004 | Supportive supervision visit 4 | Monitoring | Country_4 | 2026-04-01 | 2026-06-30 | Year 3 | Y3Q2 | 78 | 85 | 109% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C4A005 | Policy dialogue 5 | Advocacy | Country_4 | 2026-07-01 | 2026-09-30 | Year 3 | Y3Q3 | 33 | 0 | 0% | Meeting minutes; participant list | Yes | Not started | Planned for a future quarter.
OI-101 | People trained in targeted skills | C4A006 | Training workshop 6 | Training | Country_4 | 2026-10-01 | 2026-12-31 | Year 3 | Y3Q4 | 38 | 0 | 0% | Signed attendance sheet; pre/post test forms | No | Not started | Planned for a future quarter.
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Country_4
Second Verification Tracker
Activity ID | Output Indicator ID | Second Verification Type | Verification Description | Verification Date | Verification Status | Verification File Reference / Link
C4A002 | OI-101 | Phone Check | Phone Check scheduled / under review for C4A002 | 2026-01-14 | In Review | Ref/Country_4/C4A002
C4A005 | OI-104 | Site Visit | Site Visit scheduled / under review for C4A005 |  | Pending | Ref/Country_4/C4A005

## Country_5
Country_5 M&E Tracker
Output Indicator ID | Output Indicator Description | Activity ID | Activity Name | Component | Country of Implementation | Start Date | End Date | Program Year | Quarter of Implementation | Planned Number of Participants | Actual Number of Participants | % Achievement | Means of Verification (Primary) | Use Second Verification? (Yes/No) | Status | Comments / Risks / Issues
OI-101 | People trained in targeted skills | C5A001 | Training workshop 1 | Training | Country_5 | 2024-01-01 | 2024-03-31 | Year 1 | Y1Q1 | 70 | 71 | 101.4% | Signed attendance sheet; pre/post test forms | Yes | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C5A002 | Community outreach campaign 2 | Outreach | Country_5 | 2024-04-01 | 2024-06-30 | Year 1 | Y1Q2 | 75 | 72 | 96% | Activity report; photo log | No | In progress | Final attendance reconciliation pending.
OI-103 | Supportive supervision visits conducted | C5A003 | Supportive supervision visit 3 | Monitoring | Country_5 | 2024-07-01 | 2024-09-30 | Year 1 | Y1Q3 | 30 | 23 | 76.67% | Supervision checklist; visit report | No | In progress | Final attendance reconciliation pending.
OI-104 | Policy dialogues facilitated | C5A004 | Policy dialogue 4 | Advocacy | Country_5 | 2024-10-01 | 2024-12-31 | Year 1 | Y1Q4 | 35 | 45 | 128.6% | Meeting minutes; participant list | Yes | Completed | Completed as scheduled.
OI-101 | People trained in targeted skills | C5A005 | Training workshop 5 | Training | Country_5 | 2025-01-01 | 2025-03-31 | Year 2 | Y2Q1 | 40 | 46 | 115% | Signed attendance sheet; pre/post test forms | No | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C5A006 | Community outreach campaign 6 | Outreach | Country_5 | 2025-04-01 | 2025-06-30 | Year 2 | Y2Q2 | 45 | 47 | 104.4% | Activity report; photo log | No | Completed | Completed as scheduled.
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Country_5
Second Verification Tracker
Activity ID | Output Indicator ID | Second Verification Type | Verification Description | Verification Date | Verification Status | Verification File Reference / Link
C5A001 | OI-101 | Phone Check | Phone Check completed for C5A001 | 2024-04-14 | Complete | Ref/Country_5/C5A001
C5A004 | OI-104 | Site Visit | Site Visit completed for C5A004 | 2025-01-14 | Complete | Ref/Country_5/C5A004

## Country_6
Country_6 M&E Tracker
Output Indicator ID | Output Indicator Description | Activity ID | Activity Name | Component | Country of Implementation | Start Date | End Date | Program Year | Quarter of Implementation | Planned Number of Participants | Actual Number of Participants | % Achievement | Means of Verification (Primary) | Use Second Verification? (Yes/No) | Status | Comments / Risks / Issues
OI-102 | Community outreach events delivered | C6A001 | Community outreach campaign 1 | Outreach | Country_6 | 2025-07-01 | 2025-09-30 | Year 2 | Y2Q3 | 77 | 81 | 105.2% | Activity report; photo log | No | Completed | Completed as scheduled.
OI-103 | Supportive supervision visits conducted | C6A002 | Supportive supervision visit 2 | Monitoring | Country_6 | 2025-10-01 | 2025-12-31 | Year 2 | Y2Q4 | 32 | 32 | 100% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C6A003 | Policy dialogue 3 | Advocacy | Country_6 | 2026-01-01 | 2026-03-31 | Year 3 | Y3Q1 | 37 | 33 | 89.19% | Meeting minutes; participant list | Yes | In progress | Final attendance reconciliation pending.
OI-101 | People trained in targeted skills | C6A004 | Training workshop 4 | Training | Country_6 | 2026-04-01 | 2026-06-30 | Year 3 | Y3Q2 | 42 | 34 | 80.95% | Signed attendance sheet; pre/post test forms | No | In progress | Final attendance reconciliation pending.
OI-102 | Community outreach events delivered | C6A005 | Community outreach campaign 5 | Outreach | Country_6 | 2026-07-01 | 2026-09-30 | Year 3 | Y3Q3 | 47 | 0 | 0% | Activity report; photo log | No | Not started | Planned for a future quarter.
OI-103 | Supportive supervision visits conducted | C6A006 | Supportive supervision visit 6 | Monitoring | Country_6 | 2026-10-01 | 2026-12-31 | Year 3 | Y3Q4 | 52 | 0 | 0% | Supervision checklist; visit report | Yes | Not started | Planned for a future quarter.
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Country_6
Second Verification Tracker
Activity ID | Output Indicator ID | Second Verification Type | Verification Description | Verification Date | Verification Status | Verification File Reference / Link
C6A003 | OI-104 | Site Visit | Site Visit scheduled / under review for C6A003 | 2026-04-14 | In Review | Ref/Country_6/C6A003
C6A006 | OI-103 | Document Review | Document Review scheduled / under review for C6A006 |  | Pending | Ref/Country_6/C6A006

## Country_7
Country_7 M&E Tracker
Output Indicator ID | Output Indicator Description | Activity ID | Activity Name | Component | Country of Implementation | Start Date | End Date | Program Year | Quarter of Implementation | Planned Number of Participants | Actual Number of Participants | % Achievement | Means of Verification (Primary) | Use Second Verification? (Yes/No) | Status | Comments / Risks / Issues
OI-103 | Supportive supervision visits conducted | C7A001 | Supportive supervision visit 1 | Monitoring | Country_7 | 2024-01-01 | 2024-03-31 | Year 1 | Y1Q1 | 34 | 41 | 120.6% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C7A002 | Policy dialogue 2 | Advocacy | Country_7 | 2024-04-01 | 2024-06-30 | Year 1 | Y1Q2 | 39 | 42 | 107.7% | Meeting minutes; participant list | Yes | Completed | Completed as scheduled.
OI-101 | People trained in targeted skills | C7A003 | Training workshop 3 | Training | Country_7 | 2024-07-01 | 2024-09-30 | Year 1 | Y1Q3 | 44 | 43 | 97.73% | Signed attendance sheet; pre/post test forms | No | In progress | Final attendance reconciliation pending.
OI-102 | Community outreach events delivered | C7A004 | Community outreach campaign 4 | Outreach | Country_7 | 2024-10-01 | 2024-12-31 | Year 1 | Y1Q4 | 49 | 44 | 89.8% | Activity report; photo log | No | In progress | Final attendance reconciliation pending.
OI-103 | Supportive supervision visits conducted | C7A005 | Supportive supervision visit 5 | Monitoring | Country_7 | 2025-01-01 | 2025-03-31 | Year 2 | Y2Q1 | 54 | 45 | 83.33% | Supervision checklist; visit report | Yes | In progress | Final attendance reconciliation pending.
OI-104 | Policy dialogues facilitated | C7A006 | Policy dialogue 6 | Advocacy | Country_7 | 2025-04-01 | 2025-06-30 | Year 2 | Y2Q2 | 59 | 67 | 113.6% | Meeting minutes; participant list | No | Completed | Completed as scheduled.
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Country_7
Second Verification Tracker
Activity ID | Output Indicator ID | Second Verification Type | Verification Description | Verification Date | Verification Status | Verification File Reference / Link
C7A002 | OI-104 | Site Visit | Site Visit completed for C7A002 | 2024-07-14 | Complete | Ref/Country_7/C7A002
C7A005 | OI-103 | Document Review | Document Review scheduled / under review for C7A005 | 2025-04-14 | In Review | Ref/Country_7/C7A005

## Country_8
Country_8 M&E Tracker
Output Indicator ID | Output Indicator Description | Activity ID | Activity Name | Component | Country of Implementation | Start Date | End Date | Program Year | Quarter of Implementation | Planned Number of Participants | Actual Number of Participants | % Achievement | Means of Verification (Primary) | Use Second Verification? (Yes/No) | Status | Comments / Risks / Issues
OI-104 | Policy dialogues facilitated | C8A001 | Policy dialogue 1 | Advocacy | Country_8 | 2025-07-01 | 2025-09-30 | Year 2 | Y2Q3 | 41 | 51 | 124.4% | Meeting minutes; participant list | Yes | Completed | Completed as scheduled.
OI-101 | People trained in targeted skills | C8A002 | Training workshop 2 | Training | Country_8 | 2025-10-01 | 2025-12-31 | Year 2 | Y2Q4 | 46 | 52 | 113% | Signed attendance sheet; pre/post test forms | No | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C8A003 | Community outreach campaign 3 | Outreach | Country_8 | 2026-01-01 | 2026-03-31 | Year 3 | Y3Q1 | 51 | 53 | 103.9% | Activity report; photo log | No | Completed | Completed as scheduled.
OI-103 | Supportive supervision visits conducted | C8A004 | Supportive supervision visit 4 | Monitoring | Country_8 | 2026-04-01 | 2026-06-30 | Year 3 | Y3Q2 | 56 | 54 | 96.43% | Supervision checklist; visit report | Yes | In progress | Final attendance reconciliation pending.
OI-104 | Policy dialogues facilitated | C8A005 | Policy dialogue 5 | Advocacy | Country_8 | 2026-07-01 | 2026-09-30 | Year 3 | Y3Q3 | 61 | 0 | 0% | Meeting minutes; participant list | No | Not started | Planned for a future quarter.
OI-101 | People trained in targeted skills | C8A006 | Training workshop 6 | Training | Country_8 | 2026-10-01 | 2026-12-31 | Year 3 | Y3Q4 | 66 | 0 | 0% | Signed attendance sheet; pre/post test forms | No | Not started | Planned for a future quarter.
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Country_8
Second Verification Tracker
Activity ID | Output Indicator ID | Second Verification Type | Verification Description | Verification Date | Verification Status | Verification File Reference / Link
C8A001 | OI-104 | Site Visit | Site Visit completed for C8A001 | 2025-10-14 | Complete | Ref/Country_8/C8A001
C8A004 | OI-103 | Document Review | Document Review scheduled / under review for C8A004 | 2026-07-14 | In Review | Ref/Country_8/C8A004

## Dashboard
Monitoring & Evaluation Dashboard
Filters |  |  |  | Total Planned Participants |  | Total Actual Participants |  |  | % Achievement |  |  | Activities
Country | All | * |  | 2592 |  | 2162 |  |  | 83.41% |  |  | 48
Component | All | *
Output Indicator ID | All | *
Program Year | All | * |  | Completed |  | Delayed |  |  | 2nd Verification Needed |  |  | Tip: edit country sheets and refresh formulas by opening in Excel.
Quarter | All | * |  | 22 |  | 0 |  |  | 16
By Component |  |  |  |  | Status Breakdown |  |  | By Output Indicator
Component | Planned | Actual | % Ach. | Activities | Status | Count |  | Indicator | Planned | Actual | % Ach. | Activities
Training | 648 | 555 | 85.65% | 12 | Not started | 8 |  | OI-101 | 648 | 555 | 85.65% | 12
Outreach | 720 | 586 | 81.39% | 12 | In progress | 18 |  | OI-102 | 720 | 586 | 81.39% | 12
Monitoring | 648 | 524 | 80.86% | 12 | Completed | 22 |  | OI-103 | 648 | 524 | 80.86% | 12
Advocacy | 576 | 497 | 86.28% | 12 | Delayed | 0 |  | OI-104 | 576 | 497 | 86.28% | 12
[5 empty] | Cancelled | 0
By Program Quarter |  |  |  |  | By Country
Quarter | Planned | Actual | Activities |  | Country | Planned | Actual | Activities
Y1Q1 | 202 | 215 | 4 |  | Country_1 | 327 | 327 | 6
Y1Q2 | 222 | 219 | 4 |  | Country_2 | 369 | 233 | 6
Y1Q3 | 192 | 194 | 4 |  | Country_3 | 361 | 355 | 6
Y1Q4 | 212 | 219 | 4 |  | Country_4 | 353 | 271 | 6
Y2Q1 | 232 | 223 | 4 |  | Country_5 | 295 | 304 | 6
Y2Q2 | 202 | 198 | 4 |  | Country_6 | 287 | 180 | 6
Y2Q3 | 230 | 234 | 4 |  | Country_7 | 279 | 282 | 6
Y2Q4 | 200 | 209 | 4 |  | Country_8 | 321 | 210 | 6
Y3Q1 | 220 | 213 | 4
Y3Q2 | 240 | 238 | 4
Y3Q3 | 210 | 0 | 4
Y3Q4 | 230 | 0 | 4
Dashboard notes: filters work like slicers. Replace the sample rows on each country sheet with your own data inside the blue-font input cells.

## Lists
All | All | All | All | All | Not started | Yes | Document Review | Pending | Filter list locations
Country_1 | Training | OI-101 | Year 1 | Y1Q1 | In progress | No | Site Visit | In Review | A: Countries
Country_2 | Outreach | OI-102 | Year 2 | Y1Q2 | Completed |  | Phone Check | Complete | B: Components
Country_3 | Monitoring | OI-103 | Year 3 | Y1Q3 | Delayed |  | Digital Verification |  | C: Indicators
Country_4 | Advocacy | OI-104 |  | Y1Q4 | Cancelled |  |  |  | D: Program Years
Country_5 |  |  |  | Y2Q1 |  |  |  |  | E: Quarters
Country_6 |  |  |  | Y2Q2 |  |  |  |  | F: Statuses
Country_7 |  |  |  | Y2Q3 |  |  |  |  | G: Yes/No
Country_8 |  |  |  | Y2Q4 |  |  |  |  | H: Verification Types
|  |  |  | Y3Q1 |  |  |  |  | I: Verification Statuses
Y3Q2
Y3Q3
Y3Q4

## Consolidated_Data
Output Indicator ID | Output Indicator Description | Activity ID | Activity Name | Component | Country of Implementation | Start Date | End Date | Program Year | Quarter of Implementation | Planned Number of Participants | Actual Number of Participants | % Achievement | Means of Verification (Primary) | Use Second Verification? (Yes/No) | Status | Comments / Risks / Issues
OI-101 | People trained in targeted skills | C1A001 | Training workshop 1 | Training | Country_1 | 2024-01-01 | 2024-03-31 | Year 1 | Y1Q1 | 42 | 52 | 123.8% | Signed attendance sheet; pre/post test forms | No | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C1A002 | Community outreach campaign 2 | Outreach | Country_1 | 2024-04-01 | 2024-06-30 | Year 1 | Y1Q2 | 47 | 53 | 112.8% | Activity report; photo log | Yes | Completed | Completed as scheduled.
OI-103 | Supportive supervision visits conducted | C1A003 | Supportive supervision visit 3 | Monitoring | Country_1 | 2024-07-01 | 2024-09-30 | Year 1 | Y1Q3 | 52 | 54 | 103.8% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C1A004 | Policy dialogue 4 | Advocacy | Country_1 | 2024-10-01 | 2024-12-31 | Year 1 | Y1Q4 | 57 | 55 | 96.49% | Meeting minutes; participant list | No | In progress | Final attendance reconciliation pending.
OI-101 | People trained in targeted skills | C1A005 | Training workshop 5 | Training | Country_1 | 2025-01-01 | 2025-03-31 | Year 2 | Y2Q1 | 62 | 56 | 90.32% | Signed attendance sheet; pre/post test forms | Yes | In progress | Final attendance reconciliation pending.
OI-102 | Community outreach events delivered | C1A006 | Community outreach campaign 6 | Outreach | Country_1 | 2025-04-01 | 2025-06-30 | Year 2 | Y2Q2 | 67 | 57 | 85.07% | Activity report; photo log | No | In progress | Final attendance reconciliation pending.
OI-102 | Community outreach events delivered | C2A001 | Community outreach campaign 1 | Outreach | Country_2 | 2025-07-01 | 2025-09-30 | Year 2 | Y2Q3 | 49 | 41 | 83.67% | Activity report; photo log | Yes | In progress | Final attendance reconciliation pending.
OI-103 | Supportive supervision visits conducted | C2A002 | Supportive supervision visit 2 | Monitoring | Country_2 | 2025-10-01 | 2025-12-31 | Year 2 | Y2Q4 | 54 | 63 | 116.7% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C2A003 | Policy dialogue 3 | Advocacy | Country_2 | 2026-01-01 | 2026-03-31 | Year 3 | Y3Q1 | 59 | 64 | 108.5% | Meeting minutes; participant list | No | Completed | Completed as scheduled.
OI-101 | People trained in targeted skills | C2A004 | Training workshop 4 | Training | Country_2 | 2026-04-01 | 2026-06-30 | Year 3 | Y3Q2 | 64 | 65 | 101.6% | Signed attendance sheet; pre/post test forms | Yes | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C2A005 | Community outreach campaign 5 | Outreach | Country_2 | 2026-07-01 | 2026-09-30 | Year 3 | Y3Q3 | 69 | 0 | 0% | Activity report; photo log | No | Not started | Planned for a future quarter.
OI-103 | Supportive supervision visits conducted | C2A006 | Supportive supervision visit 6 | Monitoring | Country_2 | 2026-10-01 | 2026-12-31 | Year 3 | Y3Q4 | 74 | 0 | 0% | Supervision checklist; visit report | No | Not started | Planned for a future quarter.
OI-103 | Supportive supervision visits conducted | C3A001 | Supportive supervision visit 1 | Monitoring | Country_3 | 2024-01-01 | 2024-03-31 | Year 1 | Y1Q1 | 56 | 51 | 91.07% | Supervision checklist; visit report | No | In progress | Final attendance reconciliation pending.
OI-104 | Policy dialogues facilitated | C3A002 | Policy dialogue 2 | Advocacy | Country_3 | 2024-04-01 | 2024-06-30 | Year 1 | Y1Q2 | 61 | 52 | 85.25% | Meeting minutes; participant list | No | In progress | Final attendance reconciliation pending.
OI-101 | People trained in targeted skills | C3A003 | Training workshop 3 | Training | Country_3 | 2024-07-01 | 2024-09-30 | Year 1 | Y1Q3 | 66 | 74 | 112.1% | Signed attendance sheet; pre/post test forms | Yes | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C3A004 | Community outreach campaign 4 | Outreach | Country_3 | 2024-10-01 | 2024-12-31 | Year 1 | Y1Q4 | 71 | 75 | 105.6% | Activity report; photo log | No | Completed | Completed as scheduled.
OI-103 | Supportive supervision visits conducted | C3A005 | Supportive supervision visit 5 | Monitoring | Country_3 | 2025-01-01 | 2025-03-31 | Year 2 | Y2Q1 | 76 | 76 | 100% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C3A006 | Policy dialogue 6 | Advocacy | Country_3 | 2025-04-01 | 2025-06-30 | Year 2 | Y2Q2 | 31 | 27 | 87.1% | Meeting minutes; participant list | Yes | In progress | Final attendance reconciliation pending.
OI-104 | Policy dialogues facilitated | C4A001 | Policy dialogue 1 | Advocacy | Country_4 | 2025-07-01 | 2025-09-30 | Year 2 | Y2Q3 | 63 | 61 | 96.83% | Meeting minutes; participant list | No | In progress | Final attendance reconciliation pending.
OI-101 | People trained in targeted skills | C4A002 | Training workshop 2 | Training | Country_4 | 2025-10-01 | 2025-12-31 | Year 2 | Y2Q4 | 68 | 62 | 91.18% | Signed attendance sheet; pre/post test forms | Yes | In progress | Final attendance reconciliation pending.
OI-102 | Community outreach events delivered | C4A003 | Community outreach campaign 3 | Outreach | Country_4 | 2026-01-01 | 2026-03-31 | Year 3 | Y3Q1 | 73 | 63 | 86.3% | Activity report; photo log | No | In progress | Final attendance reconciliation pending.
OI-103 | Supportive supervision visits conducted | C4A004 | Supportive supervision visit 4 | Monitoring | Country_4 | 2026-04-01 | 2026-06-30 | Year 3 | Y3Q2 | 78 | 85 | 109% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C4A005 | Policy dialogue 5 | Advocacy | Country_4 | 2026-07-01 | 2026-09-30 | Year 3 | Y3Q3 | 33 | 0 | 0% | Meeting minutes; participant list | Yes | Not started | Planned for a future quarter.
OI-101 | People trained in targeted skills | C4A006 | Training workshop 6 | Training | Country_4 | 2026-10-01 | 2026-12-31 | Year 3 | Y3Q4 | 38 | 0 | 0% | Signed attendance sheet; pre/post test forms | No | Not started | Planned for a future quarter.
OI-101 | People trained in targeted skills | C5A001 | Training workshop 1 | Training | Country_5 | 2024-01-01 | 2024-03-31 | Year 1 | Y1Q1 | 70 | 71 | 101.4% | Signed attendance sheet; pre/post test forms | Yes | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C5A002 | Community outreach campaign 2 | Outreach | Country_5 | 2024-04-01 | 2024-06-30 | Year 1 | Y1Q2 | 75 | 72 | 96% | Activity report; photo log | No | In progress | Final attendance reconciliation pending.
OI-103 | Supportive supervision visits conducted | C5A003 | Supportive supervision visit 3 | Monitoring | Country_5 | 2024-07-01 | 2024-09-30 | Year 1 | Y1Q3 | 30 | 23 | 76.67% | Supervision checklist; visit report | No | In progress | Final attendance reconciliation pending.
OI-104 | Policy dialogues facilitated | C5A004 | Policy dialogue 4 | Advocacy | Country_5 | 2024-10-01 | 2024-12-31 | Year 1 | Y1Q4 | 35 | 45 | 128.6% | Meeting minutes; participant list | Yes | Completed | Completed as scheduled.
OI-101 | People trained in targeted skills | C5A005 | Training workshop 5 | Training | Country_5 | 2025-01-01 | 2025-03-31 | Year 2 | Y2Q1 | 40 | 46 | 115% | Signed attendance sheet; pre/post test forms | No | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C5A006 | Community outreach campaign 6 | Outreach | Country_5 | 2025-04-01 | 2025-06-30 | Year 2 | Y2Q2 | 45 | 47 | 104.4% | Activity report; photo log | No | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C6A001 | Community outreach campaign 1 | Outreach | Country_6 | 2025-07-01 | 2025-09-30 | Year 2 | Y2Q3 | 77 | 81 | 105.2% | Activity report; photo log | No | Completed | Completed as scheduled.
OI-103 | Supportive supervision visits conducted | C6A002 | Supportive supervision visit 2 | Monitoring | Country_6 | 2025-10-01 | 2025-12-31 | Year 2 | Y2Q4 | 32 | 32 | 100% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C6A003 | Policy dialogue 3 | Advocacy | Country_6 | 2026-01-01 | 2026-03-31 | Year 3 | Y3Q1 | 37 | 33 | 89.19% | Meeting minutes; participant list | Yes | In progress | Final attendance reconciliation pending.
OI-101 | People trained in targeted skills | C6A004 | Training workshop 4 | Training | Country_6 | 2026-04-01 | 2026-06-30 | Year 3 | Y3Q2 | 42 | 34 | 80.95% | Signed attendance sheet; pre/post test forms | No | In progress | Final attendance reconciliation pending.
OI-102 | Community outreach events delivered | C6A005 | Community outreach campaign 5 | Outreach | Country_6 | 2026-07-01 | 2026-09-30 | Year 3 | Y3Q3 | 47 | 0 | 0% | Activity report; photo log | No | Not started | Planned for a future quarter.
OI-103 | Supportive supervision visits conducted | C6A006 | Supportive supervision visit 6 | Monitoring | Country_6 | 2026-10-01 | 2026-12-31 | Year 3 | Y3Q4 | 52 | 0 | 0% | Supervision checklist; visit report | Yes | Not started | Planned for a future quarter.
OI-103 | Supportive supervision visits conducted | C7A001 | Supportive supervision visit 1 | Monitoring | Country_7 | 2024-01-01 | 2024-03-31 | Year 1 | Y1Q1 | 34 | 41 | 120.6% | Supervision checklist; visit report | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C7A002 | Policy dialogue 2 | Advocacy | Country_7 | 2024-04-01 | 2024-06-30 | Year 1 | Y1Q2 | 39 | 42 | 107.7% | Meeting minutes; participant list | Yes | Completed | Completed as scheduled.
OI-101 | People trained in targeted skills | C7A003 | Training workshop 3 | Training | Country_7 | 2024-07-01 | 2024-09-30 | Year 1 | Y1Q3 | 44 | 43 | 97.73% | Signed attendance sheet; pre/post test forms | No | In progress | Final attendance reconciliation pending.
OI-102 | Community outreach events delivered | C7A004 | Community outreach campaign 4 | Outreach | Country_7 | 2024-10-01 | 2024-12-31 | Year 1 | Y1Q4 | 49 | 44 | 89.8% | Activity report; photo log | No | In progress | Final attendance reconciliation pending.
OI-103 | Supportive supervision visits conducted | C7A005 | Supportive supervision visit 5 | Monitoring | Country_7 | 2025-01-01 | 2025-03-31 | Year 2 | Y2Q1 | 54 | 45 | 83.33% | Supervision checklist; visit report | Yes | In progress | Final attendance reconciliation pending.
OI-104 | Policy dialogues facilitated | C7A006 | Policy dialogue 6 | Advocacy | Country_7 | 2025-04-01 | 2025-06-30 | Year 2 | Y2Q2 | 59 | 67 | 113.6% | Meeting minutes; participant list | No | Completed | Completed as scheduled.
OI-104 | Policy dialogues facilitated | C8A001 | Policy dialogue 1 | Advocacy | Country_8 | 2025-07-01 | 2025-09-30 | Year 2 | Y2Q3 | 41 | 51 | 124.4% | Meeting minutes; participant list | Yes | Completed | Completed as scheduled.
OI-101 | People trained in targeted skills | C8A002 | Training workshop 2 | Training | Country_8 | 2025-10-01 | 2025-12-31 | Year 2 | Y2Q4 | 46 | 52 | 113% | Signed attendance sheet; pre/post test forms | No | Completed | Completed as scheduled.
OI-102 | Community outreach events delivered | C8A003 | Community outreach campaign 3 | Outreach | Country_8 | 2026-01-01 | 2026-03-31 | Year 3 | Y3Q1 | 51 | 53 | 103.9% | Activity report; photo log | No | Completed | Completed as scheduled.
OI-103 | Supportive supervision visits conducted | C8A004 | Supportive supervision visit 4 | Monitoring | Country_8 | 2026-04-01 | 2026-06-30 | Year 3 | Y3Q2 | 56 | 54 | 96.43% | Supervision checklist; visit report | Yes | In progress | Final attendance reconciliation pending.
OI-104 | Policy dialogues facilitated | C8A005 | Policy dialogue 5 | Advocacy | Country_8 | 2026-07-01 | 2026-09-30 | Year 3 | Y3Q3 | 61 | 0 | 0% | Meeting minutes; participant list | No | Not started | Planned for a future quarter.
OI-101 | People trained in targeted skills | C8A006 | Training workshop 6 | Training | Country_8 | 2026-10-01 | 2026-12-31 | Year 3 | Y3Q4 | 66 | 0 | 0% | Signed attendance sheet; pre/post test forms | No | Not started | Planned for a future quarter.
Formulas:
Start Date = IF(Country_1!$[Activity ID, row below]="","",Country_1!G3)
End Date = IF(Country_1!$[Activity ID, row below]="","",Country_1!H3)