## Parameters
THABAT PP – SAS BUSINESS CLINIC ¦ CONTROL PARAMETERS
Single control panel. Every threshold, capacity figure and date below feeds the rest of the workbook by formula. Yellow cells = fill these in. Change a number here and the whole system updates.
PROJECT WINDOW
Project name | THABAT PP – SAS Business Clinic BDS
Project start | 2026-06-01 | Inception. Jun–Oct 2026 window.
Project end | 2026-10-31 | Final consultancy report due.
Weeks in window | 22 | Auto-calculated from start/end.
Total SMEs (target) | 80 | Per TOR: 80+ grant-awarded SMEs.
Number of Coaches |  | DROP IN when confirmed. Drives the capacity model.
Number of Community Enablers |  | DROP IN when confirmed.
EXCEPTION THRESHOLDS (the auto-RAG engine)
Missed coaching touchpoints → AMBER | 2 | 2 consecutive misses = amber + coach recovery action.
Missed coaching touchpoints → RED | 3 | Escalation territory.
Stage at % of duration cap → AMBER | 80% | At 80% of allowed time, warn.
Stage over duration cap → RED | 100% | Over cap = red, weekly-review item.
Grant utilisation floor | 50% | Below this at checkpoint = escalate to PD.
Grant utilisation checkpoint date | 2026-08-31 | Mid-window burn-rate check.
Documentation completeness target | 80% | Below this flags amber on the SME.
CAPACITY ASSUMPTIONS (per person, per week)
Diagnostics per Coach / week | 3
BDPs per Coach / week | 2
Coaching sessions per Coach / week | 10
Field visits per Enabler / week | 8
SERVICE VOLUME (required per SME, full cycle)
Diagnostics per SME | 1
BDPs per SME | 1
Coaching sessions per SME | 12 | Weekly-ish over the cycle.
Field visits per SME | 4
REGISTRY VIEW MODE
Show columns (Grant / Delivery / Both) | Both | Use the +/- outline buttons above the Registry columns to collapse the Delivery, Doc, or Grant blocks. This cell records intent.

## Stage-Gate Definitions
STAGE-GATE DEFINITIONS — "done" is non-negotiable. A stage exits ONLY when every exit criterion is met.
Stage | Seq | Entry Criteria | Exit Criteria | Expected Duration (days) | Required Evidence | Responsible Owner | Output Document
Not Started | 0 | SME confirmed on grant list; assigned to a Coach. | Diagnostic scheduled in the calendar. |  | Assignment recorded in Registry. | Operations & Portfolio Mgr | Registry entry
Diagnostic | 1 | SME assigned; diagnostic session booked. | Diagnostic completed, written up, filed, and linked to the SME record. | 14 | Completed diagnostic report; attendance note. | Business Dev. Coach | Diagnostic Report
Business Development Plan | 2 | Diagnostic filed and signed off. | BDP APPROVED, filed, linked to SME record, AND coaching plan set. A draft is NOT an exit. | 21 | Signed/approved BDP; baseline captured. | Business Dev. Coach | Approved BDP
Coaching | 3 | Approved BDP with coaching plan in place. | Agreed coaching sessions delivered to cadence; coaching notes filed each session. | 70 | Coaching notes per session; attendance log. | Business Dev. Coach | Coaching Notes
Field Follow-up | 4 | Coaching cycle substantially delivered. | Field visit(s) completed, field notes filed, SME action items verified on-site. | 21 | Field visit notes; verification checklist. | Community Enabler | Field Visit Record
Complete | 5 | All prior gates passed; SME file complete. | All deliverables filed, compliance records complete, file audit-ready. |  | Full SME case file; sign-offs. | Operations & Portfolio Mgr | Closed SME Case File

## Governance & Exceptions
GOVERNANCE — DECISION RIGHTS & THE EXCEPTION ENGINE
You coordinate; you do not command. This separates what you DECIDE, what you RECOMMEND, and what you ESCALATE — so the system never stalls when a Coach resists.
1 · DECISION RIGHTS MATRIX
Action / Situation | You DECIDE | You RECOMMEND | ESCALATE to PD | Rule
Schedule a session within a Coach's agreed capacity band | ✔ |  |  | Yours to make, log it.
Re-slot a session inside the same state | ✔ |  |  | Within capacity bands = your call.
Rebalance caseload across Coaches in the SAME state |  | ✔ |  | Recommend; PD confirms.
Cross-STATE reallocation of SMEs or Coaches |  |  | ✔ | Requires PD approval.
Reset a stage deadline for one SME (minor slip) | ✔ |  |  | Inside tolerance, your call.
Reset milestones affecting the donor timeline |  |  | ✔ | PD owns donor-facing dates.
Repeated Coach non-adherence (after recovery action) |  |  | ✔ | Formal escalation, documented.
Grant-utilisation below floor at checkpoint |  | ✔ | ✔ | Recommend intervention + escalate.
Standard corrective action at SME level |  | ✔ |  | With Coach/Enabler; PD informed.
Engaging Mercy Corps technical counterparts |  |  | ✔ | Only as PD delegates.
2 · EXCEPTION RULES (trigger → status → required response)
Trigger | Threshold (from Parameters) | Auto-status | Required response | Decision right
Missed consecutive coaching touchpoints | ≥ amber threshold | AMBER | Coach logs recovery action within the week. | Recommend
Missed consecutive coaching touchpoints | ≥ red threshold | RED | Weekly-review item; PD notified. | Escalate
Stage time elapsed vs duration cap | ≥ amber % of cap | AMBER | Flag in weekly review; chase owner. | Decide
Stage time elapsed vs duration cap | over cap | RED | Mandatory weekly-review discussion + corrective action. | Escalate
Grant utilisation at checkpoint date | < floor % | RED | Escalate to PD with a proposed intervention. | Escalate
Documentation completeness on an SME | < target % | AMBER | Chase missing evidence before month-end report. | Decide
Compliance status = At Risk | manual flag | RED | Immediate escalation; freeze stage progression. | Escalate

## Master SME Registry
IDENTITY & ASSIGNMENT (static) | [5 empty] | DELIVERY / STAGE (dynamic) | [11 empty] | DOCUMENTATION | [6 empty] | GRANT / COMPLIANCE | [5 empty] | CONTROL
SME ID | SME Name | State | Sector | Assigned Coach | Assigned Enabler | Current Stage | Stage Entry Date | Expected Dur. (days) | Days in Stage | Stage Overdue? | Last Coaching Date | Missed Touchpoints | Last Field Visit | Next Action | Next Due Date | Dependency | Last Update | Diagnostic Filed | BDP Filed | Coaching Notes Filed | Field Notes Filed | Compliance Recs Filed | Approvals Filed | Doc Completeness % | Grant Value ($) | Grant Award Date | Grant Spent ($) | Grant Utilisation % | Utilisation Flag | Compliance Status | RAG STATUS | Open Risks
SME-001 | Kassala Grain Processing Co-op | Kassala | Processing | Coach A | Enabler 1 | Coaching | 2026-06-15 | 70 | -7 |  | 2026-07-10 | 2 | 2026-08-01 | Resolve packaging supplier | 2026-08-12 | Awaiting equipment quote | 2026-08-05 | Y | Y | Y | N | Y | N | 66.67% | 12000 | 2026-05-20 | 5200 | 43.33% |  | OK | AMBER | 0
SME-002 | River Nile Cold Storage Ltd | River Nile | Storage | Coach B | Enabler 2 | Business Development Plan | 2026-07-01 | 21 | -23 |  |  | 0 |  | Finalise approved BDP | 2026-08-10 | Diagnostic sign-off pending | 2026-08-04 | Y | N | N | N | N | N | 16.67% | 18000 | 2026-05-22 | 1500 | 8.333% |  | Gap | AMBER | 1
SME-003 | Atbara Transport Collective | River Nile | Transportation | Coach A | Enabler 2 | Diagnostic | 2026-07-20 | 14 | -42 |  |  |  |  | Complete diagnostic write-up | 2026-08-08 |  | 2026-08-03 | N | N | N | N | N | N | 0% | 9000 | 2026-05-25 | 0 | 0% |  | OK | AMBER | 0
SME-004 | Dongola Date Packaging | Northern | Packaging | Coach C | Enabler 3 | Coaching | 2026-06-10 | 70 | -2 |  | 2026-06-28 | 4 | 2026-07-22 | Recover missed sessions | 2026-08-09 | Coach availability | 2026-08-05 | Y | Y | N | N | N | N | 33.33% | 15000 | 2026-05-18 | 11000 | 73.33% |  | At Risk | RED | 1
SME-005 | Halfa Agri-Processing | Northern | Processing | Coach C | Enabler 3 | Field Follow-up | 2026-07-25 | 21 | -47 |  | 2026-07-30 | 1 | 2026-08-02 | Verify on-site action items | 2026-08-14 |  | 2026-08-06 | Y | Y | Y | Y | Y | Y | 100% | 11000 | 2026-05-20 | 9800 | 89.09% |  | OK | GREEN | 0
SME-006 | Port Sudan Storage Hub | Kassala | Storage | Coach B | Enabler 1 | Complete |  | 0 |  |  | 2026-07-18 |  | 2026-07-20 | Closed - filed | 2026-07-31 |  | 2026-07-31 | Y | Y | Y | Y | Y | Y | 100% | 20000 | 2026-05-15 | 19500 | 97.5% |  | OK | GREEN | 0
SME-007 | Kassala Sesame Cleaners | Kassala | Processing | Coach A | Enabler 1 | Coaching | 2026-06-20 | 70 | -12 |  | 2026-07-05 | 3 | 2026-07-29 | Escalate cadence breach | 2026-08-11 | Security access | 2026-08-04 | Y | Y | N | N | N | N | 33.33% | 13500 | 2026-05-21 | 3000 | 22.22% |  | OK | RED | 1
SME-008 | Shendi Packaging SME | River Nile | Packaging | Coach B | Enabler 2 | Diagnostic | 2026-07-28 | 14 | -50 |  |  | 0 |  | Book diagnostic session | 2026-08-15 |  | 2026-08-05 | N | N | N | N | N | N | 0% | 8500 | 2026-05-26 | 0 | 0% |  | OK | AMBER | 0
SME-009 | [31 empty] | 0
SME-010 | [31 empty] | 0
SME-011 | [31 empty] | 0
SME-012 | [31 empty] | 0
SME-013 | [31 empty] | 0
SME-014 | [31 empty] | 0
SME-015 | [31 empty] | 0
SME-016 | [31 empty] | 0
SME-017 | [31 empty] | 0
SME-018 | [31 empty] | 0
SME-019 | [31 empty] | 0
SME-020 | [31 empty] | 0
SME-021 | [31 empty] | 0
SME-022 | [31 empty] | 0
SME-023 | [31 empty] | 0
SME-024 | [31 empty] | 0
SME-025 | [31 empty] | 0
SME-026 | [31 empty] | 0
SME-027 | [31 empty] | 0
SME-028 | [31 empty] | 0
SME-029 | [31 empty] | 0
SME-030 | [31 empty] | 0
SME-031 | [31 empty] | 0
SME-032 | [31 empty] | 0
SME-033 | [31 empty] | 0
SME-034 | [31 empty] | 0
SME-035 | [31 empty] | 0
SME-036 | [31 empty] | 0
SME-037 | [31 empty] | 0
SME-038 | [31 empty] | 0
SME-039 | [31 empty] | 0
SME-040 | [31 empty] | 0
SME-041 | [31 empty] | 0
SME-042 | [31 empty] | 0
SME-043 | [31 empty] | 0
SME-044 | [31 empty] | 0
SME-045 | [31 empty] | 0
SME-046 | [31 empty] | 0
SME-047 | [31 empty] | 0
SME-048 | [31 empty] | 0
SME-049 | [31 empty] | 0
SME-050 | [31 empty] | 0
SME-051 | [31 empty] | 0
SME-052 | [31 empty] | 0
SME-053 | [31 empty] | 0
SME-054 | [31 empty] | 0
SME-055 | [31 empty] | 0
SME-056 | [31 empty] | 0
SME-057 | [31 empty] | 0
SME-058 | [31 empty] | 0
SME-059 | [31 empty] | 0
SME-060 | [31 empty] | 0
SME-061 | [31 empty] | 0
SME-062 | [31 empty] | 0
SME-063 | [31 empty] | 0
SME-064 | [31 empty] | 0
SME-065 | [31 empty] | 0
SME-066 | [31 empty] | 0
SME-067 | [31 empty] | 0
SME-068 | [31 empty] | 0
SME-069 | [31 empty] | 0
SME-070 | [31 empty] | 0
SME-071 | [31 empty] | 0
SME-072 | [31 empty] | 0
SME-073 | [31 empty] | 0
SME-074 | [31 empty] | 0
SME-075 | [31 empty] | 0
SME-076 | [31 empty] | 0
SME-077 | [31 empty] | 0
SME-078 | [31 empty] | 0
SME-079 | [31 empty] | 0
SME-080 | [31 empty] | 0
Formulas:
Days in Stage = IF(OR([Stage Entry Date]="",[DELIVERY / STAGE (dynamic)]="Complete",[DELIVERY / STAGE (dynamic)]=""),"",TODAY()-[Stage Entry Date])
Utilisation Flag = IF([Grant Utilisation %]="","",IF(AND(TODAY()>=Parameters!$C19,[Grant Utilisation %]<Parameters!$C18),"BELOW FLOOR",""))

## Activity & Calendar Log
ACTIVITY & CALENDAR LOG — every time-bound event. Daily instrument. Linked to the Registry by SME ID.
Activity ID | SME ID | SME Name | State | Event Type | Owner | Planned Date | Actual Date | Status | Variance (days) | Notes | Last Update
ACT-001 | SME-001 | Kassala Grain Processing Co-op | Kassala | Coaching | Coach A | 2026-08-04 |  | Planned |  |  | 2026-08-05
ACT-002 | SME-002 | River Nile Cold Storage Ltd | River Nile | Diagnostic | Coach B | 2026-06-30 | 2026-06-30 | Done | 0 |  | 2026-08-05
ACT-003 | SME-004 | Dongola Date Packaging | Northern | Coaching | Coach C | 2026-07-07 |  | Missed |  |  | 2026-08-05
ACT-004 | SME-005 | Halfa Agri-Processing | Northern | Field Visit | Enabler 3 | 2026-08-02 | 2026-08-02 | Done | 0 |  | 2026-08-05
ACT-005 | SME-007 | Kassala Sesame Cleaners | Kassala | Coaching | Coach A | 2026-07-28 |  | Missed |  |  | 2026-08-05
ACT-006 | SME-003 | Atbara Transport Collective | River Nile | Diagnostic | Coach A | 2026-08-06 |  | Planned |  |  | 2026-08-05

## Risk & Issues Register
RISK & ISSUES REGISTER — the exception layer. Reads off live delivery data. Weekly review + immediate on red.
Risk ID | SME ID | Risk Class | Description | Trigger Source | Likelihood (1-5) | Impact (1-5) | Severity | Severity RAG | Date Raised | Owner | Decision Right | Mitigation / Action | Status | Date Closed | Age (days) | Escalated to PD
RSK-001 | SME-004 | Performance | Two consecutive coaching sessions missed; SME falling behind BDP. | Adherence flag (4 missed) | 4 | 4 | 16 | RED | 2026-07-08 | Coach C | Escalate | Coach recovery plan; reschedule 2 sessions this week. | Open |  | -30
RSK-002 | SME-002 | Compliance | Diagnostic not yet filed; BDP stage stalling on sign-off. | Doc completeness 17% | 3 | 3 | 9 | AMBER | 2026-07-15 | Coach B | Recommend | Chase diagnostic sign-off before month-end report. | In Progress |  | -37
RSK-003 | PORTFOLIO | Operational | Coach headcount not confirmed; capacity model cannot be validated. | Capacity model deficit | 4 | 5 | 20 | RED | 2026-06-05 | Operations Mgr | Escalate | Confirm Coach/Enabler numbers with PD. | Open |  | 3
RSK-004 | SME-007 | Operational | Security access delays in Kassala disrupting field cadence. | Field regularity flag | 3 | 4 | 12 | AMBER | 2026-07-29 | Enabler 1 | Escalate | Cluster field visits; PD to liaise on access window. | Open |  | -51
Formulas:
Age (days) = IF([Date Raised]="","",IF([Status]="Closed",IF([Date Closed]="","",[Date Closed]-[Date Raised]),TODAY()-[Date Raised]))

## Capacity Model
CAPACITY MODEL — does the delivery math close? Auto-flags an impossible model the moment headcount goes in.
Supply (what the team can deliver over the window) vs Demand (what 80 SMEs require). Red = deficit. Fill Coaches/Enablers in Parameters to activate.
Service line | Supply (window) | Demand (window) | Balance | Utilisation | Verdict
Diagnostics | 0 | 80 | -80 |  | Enter headcount
BDPs | 0 | 80 | -80 |  | Enter headcount
Coaching sessions | 0 | 960 | -960 |  | Enter headcount
Field visits | 0 | 320 | -320 |  | Enter headcount
Reading: any 'DEFICIT' line means the current headcount cannot deliver that service across 80 SMEs in the window. Raise headcount, reduce per-SME volume, or extend timeline — and surface it to the PD.

## KPI Scorecard
KPI SCORECARD — the managerial control set. Computed live off the Registry & Activity Log.
Metric | Value | Target | What it tells you
Active SMEs (in cycle) | 8 | 80 | Headline portfolio load.
SMEs Complete | 1 | — | Throughput end-state.
Stage progression rate (past Diagnostic) | 75% | 70% | Share moved beyond diagnostic.
Overdue cases (stage past cap) | 0 | 0 | Direct red-flag count.
Coaching adherence rate | 0% | 90% | Sessions done vs scheduled.
Field visit completion rate | 100% | 90% | Field cadence control.
BDP completion rate | 62.5% | 80% | Approved BDPs across active SMEs.
Avg documentation completeness | 43.75% | 80% | Audit-readiness signal.
Open risks (count) | 4 | — | Active exception load.
Red risks (count) | 2 | 0 | Needs PD attention.
Oldest open risk (days) | 0 | <30 | Risk aging — stale = bad.
Avg grant utilisation | 41.73% | — | Burn-rate health.
WORKLOAD BY COACH (type Coach names below; caseload counts auto-fill from the Registry)
Coach name | Active caseload | Avg caseload | Imbalance flag
Coach A | 3 | 3 | balanced

## Dashboard — Executive
THABAT PP — EXECUTIVE DASHBOARD (Project Director view)
Status → variance → cause → action. Concise, decision-oriented. All figures auto-update from the Registry.
ACTIVE SMEs |  | COMPLETE |  | OVERDUE CASES | OPEN RISKS |  | RED RISKS
8 |  | 1 |  | 0 | 4 |  | 2
SMEs BY STAGE |  |  |  |  | RAG DISTRIBUTION
DECISIONS NEEDED FROM PD
Risks flagged for escalation (open): 3 ¦ Red risks: 2 ¦ See Risk & Issues Register, filter Decision Right = Escalate.
PIPELINE MOVEMENT |  |  |  |  | SMEs BY STATE
_stage
Not Started | 0 |  | Kassala | 3 | GREEN | 2
Diagnostic | 2 |  | River Nile | 3 | AMBER | 4
Business Development Plan | 1 |  | Northern | 2 | RED | 2
Coaching | 3
Field Follow-up | 1
Complete | 1
Diagnostics filed | 6
BDPs filed | 5
In coaching | 3
In field follow-up | 1
Complete | 1

## Dashboard — Operational
THABAT PP — OPERATIONAL DASHBOARD (your delivery cockpit)
Detailed control view. Run the work from here: adherence, workload, documentation, overdue, live risks.
STAGE PROGRESSION |  | COACHING ADHERENCE |  | FIELD COMPLETION |  | BDP COMPLETION |  | DOC COMPLETENESS
75% |  | 0% |  | 100% |  | 62.5% |  | 43.75%
WORKLOAD BY COACH
Coach | Caseload | Flag
Coach A | 3 | balanced
0
0
0
0
0
0
0
DOCUMENTATION GAPS (missing = count of 'N' or blank)
Document | Missing
Missing diagnostics | 2
Missing BDPs | 3
Missing coaching notes | 5
Missing field notes | 6
Missing compliance recs | 5
Missing approvals | 6
SCHEDULE ADHERENCE (from Activity & Calendar Log)
Coaching done | 0 |  | Coaching missed | 2 |  | Field done | 1
Overdue stages | 0 |  | Planned (upcoming) | 2 |  | Oldest open risk (d) | 0
LIVE OPEN RISKS (top of register)
Risk ID | SME | Class | Severity RAG | Owner | Decision Right | Status | Age (d)
RSK-001 | SME-004 | Performance | RED | Coach C | Escalate | Open | -30
RSK-002 | SME-002 | Compliance | AMBER | Coach B | Recommend | In Progress | -37
RSK-003 | PORTFOLIO | Operational | RED | Operations Mgr | Escalate | Open | 3
RSK-004 | SME-007 | Operational | AMBER | Enabler 1 | Escalate | Open | -51